## Isues
Story Number | Epic | Title | Acceptance Critera | Sprint | Assignee | Status
MC-100 | Database | Design Documentation for databse schema and Tables | Design Database shema and tables 1. Store Users details User name, address, credentials, cart 2. Store Product details Product categories Product details 3. orders order detilas and tracking | Sprint1 | Lok | Done
MC-101 | Database | Create Database project and create Git Repo | based on MS-100 story documentation create Database project create Git Repor my-cart-databse | Sprint1 | Lok | Inprogress
MC-102 | Common | create MyCart repo and intial solution | create emprty python project create Git Repor my-cart and commiit empty python project | BackLog |  | None
MC-103 | User Manamgement | create registration screen | create registration screen with below fieds Name mail confirm mail password address Register button | BackLog |  | None
MC-104 | User Manamgement | create Login screen | create registration screen with below fieds mail password Login button | BackLog |  | None
MC-105 | Api | create Api documentation | Design Database shema and tables 1. create/update/delete Users details 2. create/update/delete Products categories 3. create/update/delete Products | BackLog |  | None
MC-106 | Api | create repo and Test End point for api and commit | create my-cart-api repo and initial api solution | BackLog |  | None
MC-107 | Api | create end point for Authenticate user | it takes user mail and password and authenticate | BackLog |  | None
MC-108 | Api | create end point for create user | it takes user details and store it in databse | BackLog |  | None
MC-109 | Api | create end point for create product category | it takes the category name and create | BackLog |  | None
MC-110 | Api | create end point for update product category | it takes new category name and update | BackLog |  | None
MC-111 | Api | create end point for create product | it takes the category name and product details create | BackLog |  | None
MC-112 | Api | create end point for update product | it takes the updated product details and update | BackLog |  | None
MC-113 | Api | create end point for get all products | it returns the all products | BackLog |  | None
MC-114 | Product Manamgement | create common layout and header |  | BackLog |  | None
MC-115 | Product Manamgement | display all products | Should display all products | BackLog |  | None